## SPS Suport & Development
SPS Support & Development Planing For 2017
|  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
| Audit Scoreboard | Responsibility | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Discussion on Framework & Business Module | Marketing/SPS Support
2 | Prepare Proposal | Marketing/SPS Support
3 | Sent 20 Proposal to client till march | Marketing/SPS Support
4 | Follow up / Meeting / Presentation | Marketing/SPS Support
5 | Customization based on client request | SPS Support/ Programmer
SPS SAGA Bernama
1 | Setup Environment | Programmer
2 | Library | Programmer
3 | DB Design ERD | Programmer
4 | Prototype | SPS Support/ Programmer
5 | Engine | Programmer
6 | User Manual | SPS Support/ Programmer
7 | Testing | SPS Support/ Programmer
SPS System
1 | Study/Enhancemen/Update Version | SPS Support/ Programmer
2 | Sent Update Version | SPS Support/ Programmer
3 | Update Manual Book | SPS Support
SPS in UMT
1 | Discussion With UMT | SPS Support
2 | Discussion / Preparation on Material | SPS Support
3 | Enchement on SPS student version | SPS Support/ Programmer
4 | Marketing & Promotion | Marketing/ Support
5 | Training Start | SPS Support
SPS Lite - Tekun
1 | Study/Enhancement/Update Version
2 | Meet all manager Tekun | Marketing
3 | Enhancement support process | SPS Support
E-Voting System
1 | Developme E-Voting System-Cloud | Programmer
| Testing | Support
2 | Discussion on Framework & Business Module | Marketing/SPS Support
3 | Prepare Proposal | Marketing/SPS Support
4 | Sent 10 Proposal to client till march | Marketing/SPS Support
5 | Follow up / Meeting / Presentation | Marketing/SPS Support
6 | Customization based on client request | SPS Support/ Programmer
SPS in UiTM
1 | Discussion With UMT | SPS Support
2 | Discussion / Preparation on Material | SPS Support
3 | Training Start | SPS Support/ Programmer
SPS Cloud
Development
Testing

## SPS Marketing
SPS Marketing Planing For 2017
|  |  | February | [12 empty] | March
| Responsibility | Status | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Social Media
1. FB Ads Seminar | Hanif | Registered | bar: February 25
2. Update Social Media | Hanif
i) Products Promotion | Iskandar/Hanif
ii) Products Features | Iskandar/Hanif | bar: February 20
iii) Products Testimoni | Iskandar/Hanif
iv) Product Copy Writing | Iskandar/Hanif
iv) Dealership Programme | Iskandar/Hanif
Email Blasting
1. Email Blasting | M&S Teams
i) Products Promotion | M&S Teams
ii) Products Features | M&S Teams
iii) Products Testimoni | M&S Teams
iv) Dealership | M&S Teams
Telemarketing
1. Prepare Script | M&S Teams
2. Call - 50 per day | M&S Teams
3. Email follow Up | M&S Teams
Dealership Programe
1. Re-Engineer Dealership Program
Pre requisite Criteria
Minimum Re-Stock
2. Rewards Program
3. Dealership Appreciation Nights
Event Based Marketing
1. Listing all Event
2. Event Participation
3. Lead Generation
4. Email & Follow Up