## GST
Req.No | Name | Customisation - refer to latest GST Compliance Report | Findings | Remark by GST Consultant | CMI Comments 8th Jan Meeting | Remark by GST Consultant 15th Jan 2018
1 | Company Setup | GST Customisation | Will capture as a static information to display in invoice reports. | Cannot be static information as some of the GST information is subjected to change.
2 | GST Setup | GST Customisation | Customised GST Screen | Refer to latest GST Compliance Report
3 | Mapping of GST Tax Codes with GST-03 Return | Not in CNS Scope | This has to be handled in Swinburne Finance system. There are values which are not part of CNS like "Total value of goods imported under approved trader scheme" etc. | Vendor still has to prepare the mapping of GST Tax Codes with GST-03 Return for student income and related items as these items are NOT managed under Swinburne Finance System where no details/records of income can be produced. The mapping of GST Code with GST 03 Return for non student income and related items which are item no 6a, 6b, 11, 13,14, 15, 16 can be excluded. | CMI will list down the fields for which data can be retrieved from CNS and get it verified by Swinburne. This activity is a part of the implementation phase where we need to detail the mappings. | Agreed
4 | Account Code Setup | GST Customisation | Customised GST Screen | Refer to latest GST Compliance Report
5 | Department Code Setup | GST Customisation | Customised GST Screen | Refer to latest GST Compliance Report
6 | Project Code Setup | GST Customisation | Customised GST Screen | Refer to latest GST Compliance Report
7 | Transaction Code Setup | GST Customisation |  | Refer to latest GST Compliance Report
8 | Customer/Student Setup | CNS Standard Product offering | New students created in CNS will be given in a feed file to be created as customer in Swinburne Finance system. | Refer to latest GST Compliance Report, the following fields are also required: Customer BRN: Business Registration Number of customer (if any) Date GST Status Verified: Date GST status last checked (if any) Customer GST No: GST Registration Number of customer (if any) | Fields will be provided in student record for saving these details. A detailed specification for the same is being built as a part of the implementation phase. | Agreed
9 | Currency Setup |  |  | . | CampusNexus Student system does not support Multi currency as of now and hence will not be available in the current implementation . Multi-currency support is in the product roadmap and will be scheduled for release in the future versions of the product. This will be made available to Swinburne on release. | Agreed
10 | Student Account Lists (Billing Methods) | GST Customisation | GST information to be captured for each transaction code in the ledger card | Refer to latest GST Compliance Report
11 | Student Ledger Setup | GST Customisation | Addition and deletion of column in Student Ledger card | Refer to latest GST Compliance Report
12 | Post Charges (INV,DN,CN,TI,TDN,TCN,MTI,STI,MDN and MCN) | GST Customisation | 1. Add multiple charge to one invoice 2. Payment screen included 3. Multiple payment option 4. Invoice for each Transaction type | Refer to latest GST Compliance Report New format for invoices/debit notes/credit notes will be furnished
13 |  | GST Customisation | GST related fields for new charge/CN/DN | Refer to latest GST Compliance Report
13 | Post Payments | GST Customisation | Multiple Payment method | Refer to latest GST Compliance Report
14 |  | GST Customisation | GST related fields for new payment/CN/DN | Refer to latest GST Compliance Report
14 | Adjust Transactions | GST Customisation | Multiple charge in one transaction | Refer to latest GST Compliance Report
15 |  | GST Customisation | GST related fields available in a transaction to edit | Refer to latest GST Compliance Report
15 | Process Tuition Discounts | GST Customisation | Upload student for discount | Refer to latest GST Compliance Report
16 |  | GST Customisation | GST information in "process Tuition discount". | Refer to latest GST Compliance Report
16 | Scholarship (To rename to Award/Bursary/Rebate) | GST Customisation | GST related fields while setting up Scholarship | Refer to latest GST Compliance Report
17 | GST Report | GST Reports | Finance Report. | Refer to latest GST Compliance Report
18 | GST Report Summary | GST Reports | Finance Report. | Refer to latest GST Compliance Report
19 | GST Tax Amount Variance Report | GST Reports | Report from student data | Refer to latest GST Compliance Report
20 | Transaction Report | GST Reports | Report from student data | Refer to latest GST Compliance Report
21 | Invoice Listing (INV/TI/MTI/STI) | GST Reports | Report from student data | Refer to latest GST Compliance Report
22 | Debit Note Listing (DN/TDN/MDN) | GST Reports | Report from student data | Refer to latest GST Compliance Report
23 | Credit Note Listing (CN/TCN/MCN) | GST Reports | Report from student data | Refer to latest GST Compliance Report
24 | Receipt Listing | GST Reports | Report from student data | Refer to latest GST Compliance Report
25 | Student Outstanding Report | GST Reports | Report from student data | Refer to latest GST Compliance Report
26 | Student Statement | GST Customisation | Student portal - Account section. Ledger card view Invoice/Receipt | Refer to latest GST Compliance Report
27 | File Format Definition for GST Audit File (GAF) | Not in CNS Scope | This has to be handled in Swinburne Finance system. There are values which are not part of CNS like record type "P", "S" etc. | The vendor still has to prepare the GST Audit File (GAF). In GST Audit File it consists of 5 types of record. i) C = Company ii) P = Purchase iii) S = Supply iv) L = Ledger v) F = Footer The P Records Element which contains the value of Purchase that is not related to CNS system can be excluded. GAT file is required for student income and related items under CNS system as these items are NOT managed under Swinburne Finance System where no details/records of income can be produced. In conclusion, Swinburne will have 2 types of GAF File - one generated from CNS system for student income and related items and another one generated from Swinburne Finance System for other transactions not managed by CNS system. | CMI will list down the fields for which data can be retrieved from CNS and get it verified by Swinburne. A detailed specification for the same is being built as a part of the implementation phase. | Agreed
28 | Bad Debt | GST Customisation | 1. Payment reminder – 3 times – Manual 2. Remind Account team to claim remaining GST from RMCD after 6 months and 3 reminder to student | Refer to latest GST Compliance Report In addition, the system must be able to auto-calculated the Bad Debt Relief/Recovery and also the relevant recording in the system. | Bad debt relief and recovery process will be supported in the system by manual entry of negative charges to offset the ledger balance which will result in GST relief. The system will also have a manual procedure to re-instate the charge manually. As discussed, given that there is no way to differentiate if the payment being received is for an outstanding or an advance, automation of the process will not be possible. | Agreed with condition. The result must comply with GST requirement.
29 | Deposit/Advance payment received | GST Customisation | Return Deposit, will handle the refund scenario with students in CNS. Forfeit deposit and Security deposit to be handled in Finance system. Invoicing of Application fee will be handled. | Refer to latest GST Compliance Report | There are 3 deposit related scenarios which will be covered – a) Forfeit deposit b) Security deposit c) Return deposit Security deposit and return deposit in the student context are very similar and will handled through the refund functionality. | Agreed
30 | System Access | CNS Standard Product offering | Will be provided as part of CNS | Refer to latest GST Compliance Report
31 | Data Security Control / Audit Trail | CNS Standard Product offering | Audit track related to Student accounts will be provided. Changes in Journal entry will not be handled | Refer to latest GST Compliance Report Controls to prevent any editing and deleting of entries originally recorded. Changes to recorded entries should be adequately documented with information such as: i. Person making modifications ii. Date of change iii. Previous & Current entry details | This functionality is available in CNS. Only the Database administrator will have access to this data in the database. | Agreed with condition. The vendor must produces Audit Trail Report viewable for Admin, Royal Malaysian Customs Department (RMCD) or any other authorities body.
32 | Backup and Restore Management | CNS Standard Product offering | Will be provided as part of hosting compliant | Refer to latest GST Compliance Report
33 | Currency Conversion | CNS Standard Product offering | As discussed, student receivables all managed in MYR. Hence this is not Applicable. | Expectation for Currency Conversion has been updated, refer to latest GST Compliance Report | CampusNexus Student system does not support Multi currency as of now and hence will not be available in the current implementation . Multi-currency support is in the product roadmap and will be scheduled for release in the future versions of the product. This will be made available to Swinburne on release. | Agreed
34 | Training, User guide and Product Knowledge | CNS Standard Product offering | Will be provided after training session | Refer to latest GST Compliance Report
35 | Keeping of Records | CNS Standard Product offering | In system we keep the records for lifetime so we will meet the criteria of 8 year. In Data Migration we will start with the opening balances so we wont have the previous transactional records. | Refer to latest GST Compliance Report
Note on B10: ymwong: New item added