## Status report
Status PI1M Report
No | Zone | State | PI1M location | Promotion Status |  | Training Status |  |  |  | Remarks
|  |  |  | Date | Activities | Total pax | Passed | Failed | Activities
1 | 1 | Perak | Kuala Kangsar | 2017-03-15 | Public relationship status | 22 | 20 | 2
5 |  | Kedah | Yan | 2016-04-12 | Public relationship status | 21 | 15 | 6
6 |  | Perlis | Kangar | 2017-03-22 | Participation event | 20 | 17 | 4
7 |  | Pulau Pinang | Goergetown | 2016-04-19 | Broadcast promotion | 23 | 20 | 3
8 | 2 | Selangor | Tanjung Karang | 2016-05-20 | Online promotion - Facebook / Instagram | 20 | 20 | 0
9 |  |  | Gombak | 2017-05-17 | Road show | 20 | 18 | 2 |  | Roadshow to Sekolah Tanjung Karang
10 |  | K.Lumpur | Bangsar | 2017-05-04 | Broadcast promotion | 20 | 11 | 9 | Training on 12/6/17
11 |  | Negeri Sembilan | Kuala Pilah | 2016-05-25 | Participation event | / | / | / | Training will be conduct on 25/8/17 | To be disscused on training session plan
12 |  | Melaka | Air Molek | 2016-05-28 | Participation event | / | / | / | Training will be conduct on 5/8/17 | To be disscused on training session plan
13 |  | Johor | Johor Bahru | 2016-06-03 | Online promotion - Facebook / Instagram | / | / | / | Training will be conduct on 28/8/17 | To be disscused on training session plan
14 | 3 | Kelantan | Pasir Mas | 2016-06-05 | Online promotion - Facebook / Instagram | / | / | / | Training will be conduct on 12/9/17 | To be disscused on training session plan
15 |  | Terengganu | Kemamaman | 2016-06-17 | Broadcast promotion | / | / | / | Training will be conduct on 17/9/17 | To be disscused on training session plan
16 |  | Pahang | Jenderam Hilir | 2016-06-25 | Participation event | / | / | / | Training will be conduct on 23/9/17 | To be disscused on training session plan
17 | 4 | Sabah | Kota Kinabalu | 2016-07-23 | Roadshow | / | / | / | Training will be conduct on 24/10/17 | To be disscused on training session plan
18 | 5 | Sarawak | Kuching | 2016-07-28 | Roadshow | / | / | / | Training will be conduct on 29/10/17 | To be disscused on training session plan