## Sheet1
Month | January 2016 |  |  |  | February 2016 |  |  |  | March-June 2016 |  |  |  | July 2016 |  |  |  | August 2016 |  |  |  | September-October 2016 |  |  |  | November 2016 |  |  |  | December 2016
Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Project Planning
Finalize program module
UNITEN approval on module
Finalize MOU
MOU signing
2. Program preparation
Program introduction
Student registration
Booking of Accounting Lab
Installtation of SPS
Testing and Configurations
Class Scheduling
Registration closing
Completion of teaching kit.
3. Program Operation
Class commence group 1 & 2
SPS Workshop
GST Workshop
Class revision
Exam
Marking
Finalize results
Certification Ceremony
4 Monitoring
Enrollment
Attendance
Budget monitoring
5. Assessmeent
Program review meeting
University feedback
Program improvements