## Sheet1
SPS Development Checklist
Module |  | 13/10 - 17/10 |  |  |  |  | Priority | Date Started | Date Completed | 20/10 - 24/10 |  |  |  |  | 27/10 - 31/10 |  |  |  |  | 03/11 - 07/11 |  |  |  |  | PLAN | INDICATOR
|  | 13 | 14 | 15 | 16 | 17 |  |  |  | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | TESTING | 1
Admin | [24 empty] | IN PROGRESS | 2
| User Master /Add / Edit / Deleted | 3 | [22 empty] | COMPLETED | 3
| User Access Right /Edit | 2
| Log Report | 3
Backup | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
DB Optimize | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
General Setup
| Employee Setup /New/Edit/List | 3
| Agent Setup/New/Edit/Deleted/List | 1
| Master Code/New/Edit/Deleted/List | 1
| Project Setup New/Edit/Deleted/List | 1
| Terms Setup/New/Edit/Deleted/List | 1
| Bank Setup/New/Edit/Deleted/List | 1
| Ship to Setup/New/Edit/Deleted/List | 1
Department Setup/New/Edit/Deleted/List
Section Setup/New/Edit/Deleted/List
Company Setup
| Create /New/Edit/List/Deleted | 2 | [22 empty] | Deleted pending
| Chart of Account Setup | 2 | [22 empty] | Sample not completed download
| System General Setup/Edit | 1
| Form Setup/Edit | 3
Module : General Ledger
Transaction
Journal Entry | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Duplicate Journal | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Reverse Journal | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Posting Journal | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Payment | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Payment Confirm | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Receive | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Receive Confirm | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Year End Close | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Report | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Account Balance Summary | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Trial Balance | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Trial Balance Fiscal Year | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Statement of Financial Position | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Statement of Comprehensive Income | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Unpost Journal List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Posted Journal List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Bank Reconciliation | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Payment List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Received List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Budget List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Setup
Financial Year Calendar
Financial Year Calendar List
Budget Entry | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Currency Conversion | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Chart Of Account
Module : Account Receivable
Transaction
Sales Invoice | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Direct Sales Invoice | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Invoice Copy | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Invoice Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Debit Note - New | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Debit Note Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Credit Note | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Credit Note Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Customer Payment Received | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Customer Payment Received Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Cash Sale | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Cash Sale Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Reports
Sales Invoice List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Debit Note List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Credit Note List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Payment Received List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Customer Statement /Print All & Details | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
AR Summary | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Cash Sales List/Print All & Details | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Setup
Customer Setup
Module : Account Payable
Transaction
Purchase Invoice | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Direct Purchase Invoice - New/Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Copy Purchase Invoice | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Invoice Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Debit Note - New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Debit Note Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Credit Note - New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Credit Note Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Payment Advice | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Payment Advice Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Cash Purchase - New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Cash Purchase Confirm- New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Reports
Purchase Invoice List / Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Debit Note List / Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Credit Note List /Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Payment Advice List | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Statement List /Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Cash Purchase List/Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Setup
Supplier Setup | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Module : Sales Order
Transaction
Sales Quotation | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Order | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Delivery Order | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Delivery Order Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Reports
Sales Price | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Quotation List | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Order List | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Delivery Order List | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales By Customers | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Yearly Sales By Customers | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales By Item | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Orders By Customers | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Orders By Item | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Outstanding Sales Orders By Item | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Setup
Customer Setup | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Pricing | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Module : Purchasing
Transaction
Purchase Order - New, Edit | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Order - Confirm | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Receive | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Receive Item - Confirm | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Reports
Purchase Pricing , Print All & Details | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Order List , Print All & Details | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Received List | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Order Cancel | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Received Cancel | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Outstanding GRN Report | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Setup
Suppliers Setup | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Pricing | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
| Unit Of Measures | [23 empty] | Delete
| UOM Conversion List | [23 empty] | Delete
Module : Inventory Control | [25 empty] | `
Transaction
Location Transfer - List/Add/Edit | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Location Transfer Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Item Count And Adjust | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Item Count And Adjust Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Reports
Item Details
Location Transfer List,Print
Item Adjustment List, Print
Inventory Planning Report
Inventory Valuation Report
Stock Check Report - List/Print
Stock Count Sheet
GRN Valuation Report
Inventory Sales Report
Outstanding GRN Report
Inventory Movement Report
Inventory List
Inventory Statement
Setup
Item Category | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Item Type | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Item Setup | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Location Master | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Unit Of Measure | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
UOM Conversion List
Module: Good & Services Tax
Transaction
GAF Files Process | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Relief | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Relief Confirm | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Recover | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Recover Confirm | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Reports
GST Report | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
GST 03 | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Relief List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Recover List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Setup
Tax Table List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Tax Class List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Tax Group List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Tax Type List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Module : Zakat & Wakaf
Transaction
Zakat Calculation | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf Calculation | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Reports | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Center | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Group List | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Summary | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf List | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Setup | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab Details | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab Group | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Centre | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf Setup | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf Centre | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Module : UserGuide
UserGuide Content Entry
UserGuide Content Display
UserGuide Topic Entry
UserGuide Topic Display
UserGuide Content Download
UserGuide Video Play
UserGuide Search
UserGuide Language
Final Stage
iFlow
Module homepage
Database reindexing and performance tune up
User Manual
Installation/distribution step and procedure
| Prepared by : Aizat |  |  | Date : 13/10/2014
Note on A3: IT: as at 24/6/2014 13:00

## summary
/
iAccount Development Checklist
| Module | Status | [5 empty] | 20/10 - 24/10
|  | Dev | UT | FT | MC | SAT | UAT
| Admin | FALSE | FALSE |  |  |  | / | 0%
| General Setup | [5 empty] | / | 0%
| Company Setup | [5 empty] | / | 0%
| Module : General Ledger | [5 empty] | / | 0%
| Module : Account Receivable | [5 empty] | / | 0%
| Module : Account Payable | [5 empty] | / | 0%
| Module : Inventory Control | [5 empty] | / | 0%
| Module : Purchasing | [5 empty] | / | 0%
| Module: Good & Services Tax | [5 empty] | / | 0%
| Module : Sales Order | [5 empty] | / | 0%
| Module : Zakat & Wakaf | [5 empty] | / | 0%
| #REF! | [5 empty] | / | 0%
| Final Stage | [5 empty] | / | 0%
| average % | 0 | 0 | 0 | 0 | 0 | #REF! | 0%
Note on A2: IT: as at 12/6/2014 13:00

## Sheet2
USER ACCEPTANCE TEST : iACCOUNTS
Company Name | :
Module | :
SCENARIO |  | PROBLEM / RESULT | ACTION