## Sheet1
iAccount Development Checklist
Module |  | 13/10 - 17/10 |  |  |  |  | Priority | Date Started | Date Completed | 20/10 - 24/10 |  |  |  |  | 27/10 - 31/10 |  |  |  |  | 03/11 - 07/11 |  |  |  |  | 10/11 - 14/11 |  |  |  |  | 17/11 - 21/11
|  | 13 | 14 | 15 | 16 | 17 |  |  |  | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Admin
| User Master /Add / Edit / Deleted | [34 empty] | plan
| User Access Right /Edit | [33 empty] | 1 | testing
| Log Report | [33 empty] | 2 | pending
| Backup | [33 empty] | 3 | complete | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
DB Optimize | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
General Setup
Employee Setup /New/Edit/List
Agent Setup/New/Edit/Deleted/List
Master Code/New/Edit/Deleted/List
Project Setup New/Edit/Deleted/List
Terms Setup/New/Edit/Deleted/List
Bank Setup/New/Edit/Deleted/List
Ship to Setup/New/Edit/Deleted/List
Department Setup/New/Edit/Deleted/List
Section Setup/New/Edit/Deleted/List
Company Setup
Create /New/Edit/List/Deleted
Chart of Account Setup
System General Setup/Edit
Form Setup/Edit
Module : General Ledger | bar: 20/10 - 24/10 20 to 27/10 - 31/10 30; 03/11 - 07/11 3 to 03/11 - 07/11 5; 03/11 - 07/11 7 to 10/11 - 14/11 12; 17/11 - 21/11 17 to 17/11 - 21/11 19
Transaction
Journal Entry | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Duplicate Journal | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Reverse Journal | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Posting Journal | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Payment | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Payment Confirm | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Receive | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Receive Confirm | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Year End Close | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Report | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Account Balance Summary | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Trial Balance | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Trial Balance Fiscal Year | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Statement of Financial Position | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Statement of Comprehensive Income | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Unpost Journal List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Posted Journal List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Bank Reconciliation | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Payment List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Other Received List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Budget List | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Setup
Financial Year Calendar
Financial Year Calendar List
Budget Entry | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Currency Conversion | bar: 27/10 - 31/10 30 to 27/10 - 31/10 31
Chart Of Account
Module : Account Receivable | bar: 20/10 - 24/10 20 to 27/10 - 31/10 30; 03/11 - 07/11 3 to 03/11 - 07/11 5; 03/11 - 07/11 7 to 10/11 - 14/11 12; 17/11 - 21/11 17 to 17/11 - 21/11 19
Transaction
Sales Invoice | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Direct Sales Invoice | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Invoice Copy | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Invoice Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Debit Note - New | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Debit Note Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Credit Note | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Credit Note Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Customer Payment Received | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Customer Payment Received Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Cash Sale | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Cash Sale Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Reports
Sales Invoice List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Debit Note List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Credit Note List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Payment Received List / Print | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Customer Statement /Print All & Details | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
AR Summary | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Cash Sales List/Print All & Details | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Setup
Customer Setup
Module : Account Payable | bar: 20/10 - 24/10 20 to 10/11 - 14/11 14
Transaction
Purchase Invoice | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Direct Purchase Invoice - New/Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Copy Purchase Invoice | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Invoice Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Debit Note - New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Debit Note Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Credit Note - New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Credit Note Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Payment Advice | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Payment Advice Confirm | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Cash Purchase - New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Cash Purchase Confirm- New,Edit | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Reports
Purchase Invoice List / Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Debit Note List / Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Purchase Credit Note List /Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Payment Advice List | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Supplier Statement List /Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Cash Purchase List/Print | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Setup
Supplier Setup | bar: 20/10 - 24/10 22 to 20/10 - 24/10 24
Module : Sales Order | bar: 20/10 - 24/10 20 to 10/11 - 14/11 14
Transaction
Sales Quotation | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Order | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Delivery Order | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Delivery Order Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Reports
Sales Price | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Quotation List | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Order List | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Delivery Order List | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales By Customers | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Yearly Sales By Customers | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales By Item | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Orders By Customers | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Orders By Item | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Outstanding Sales Orders By Item | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Setup
Customer Setup | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Sales Pricing | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Module : Purchasing | bar: 20/10 - 24/10 20 to 10/11 - 14/11 14
Transaction
Purchase Order - New, Edit | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Order - Confirm | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Receive | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Receive Item - Confirm | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Reports
Purchase Pricing , Print All & Details | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Order List , Print All & Details | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Received List | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Order Cancel | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Received Cancel | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Outstanding GRN Report | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Setup
Suppliers Setup | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Purchase Pricing | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
| Unit Of Measures | [33 empty] | Delete
| UOM Conversion List | [33 empty] | Delete
Module : Inventory Control | [34 empty] | ` | bar: 20/10 - 24/10 20 to 27/10 - 31/10 30; 03/11 - 07/11 3 to 03/11 - 07/11 5; 03/11 - 07/11 7 to 10/11 - 14/11 12; 17/11 - 21/11 17 to 17/11 - 21/11 19
Transaction
Location Transfer - List/Add/Edit | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Location Transfer Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Item Count And Adjust | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Item Count And Adjust Confirm | bar: 27/10 - 31/10 27 to 27/10 - 31/10 29
Reports
Item Details | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Location Transfer List,Print | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Item Adjustment List, Print | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Inventory Planning Report | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Inventory Valuation Report | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Stock Check Report - List/Print | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Stock Count Sheet | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
GRN Valuation Report | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Inventory Sales Report | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Outstanding GRN Report | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Inventory Movement Report | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Inventory List | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Inventory Statement | bar: 20/10 - 24/10 20 to 03/11 - 07/11 7
Setup
Item Category | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Item Type | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Item Setup | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Location Master | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
Unit Of Measure | bar: 20/10 - 24/10 20 to 20/10 - 24/10 21
UOM Conversion List
Module: Good & Services Tax
Transaction
GAF Files Process | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Relief | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Relief Confirm | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Recover | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Recover Confirm | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Reports
GST Report | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
GST 03 | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Relief List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Bad Debt Recover List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Setup
Tax Table List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Tax Class List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Tax Group List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Tax Type List | bar: 03/11 - 07/11 3 to 03/11 - 07/11 5
Module : Zakat & Wakaf | bar: 20/10 - 24/10 20 to 10/11 - 14/11 14
Transaction
Zakat Calculation | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf Calculation | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Reports | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Center | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Group List | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Summary | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf List | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Setup | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab Details | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Nisab Group | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Zakat Centre | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf Setup | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Wakaf Centre | bar: 03/11 - 07/11 6 to 03/11 - 07/11 7
Module : UserGuide
UserGuide Content Entry
UserGuide Content Display
UserGuide Topic Entry
UserGuide Topic Display
UserGuide Content Download
UserGuide Video Play
UserGuide Search
UserGuide Language
Final Stage | bar: 20/10 - 24/10 20 to 10/11 - 14/11 14
iFlow
Module homepage
Database reindexing and performance tune up
User Manual
Installation/distribution step and procedure
Note on A3: IT: as at 24/6/2014 13:00

## summary
/
iAccount Development Checklist
| Module | Status | [5 empty] | 20/10 - 24/10
|  | Dev | UT | FT | MC | SAT | UAT
| Admin | FALSE | FALSE |  |  |  | / | 0%
| General Setup | [5 empty] | / | 0%
| Company Setup | [5 empty] | / | 0%
| Module : General Ledger | [5 empty] | / | 0%
| Module : Account Receivable | [5 empty] | / | 0%
| Module : Account Payable | [5 empty] | / | 0%
| Module : Inventory Control | [5 empty] | / | 0%
| Module : Purchasing | [5 empty] | / | 0%
| Module: Good & Services Tax | [5 empty] | / | 0%
| Module : Sales Order | [5 empty] | / | 0%
| Module : Zakat & Wakaf | [5 empty] | / | 0%
| #REF! | [5 empty] | / | 0%
| Final Stage | [5 empty] | / | 0%
| average % | 0 | 0 | 0 | 0 | 0 | #REF! | 0%
Note on A2: IT: as at 12/6/2014 13:00

## Sheet2
USER ACCEPTANCE TEST : iACCOUNTS
Company Name | :
Module | :
SCENARIO |  | PROBLEM / RESULT | ACTION