## Sheet1
iAccount Development Checklist
Module |  | Created By | [5 empty] | Priority | Date Started | Date Completed | Status | [5 empty] | Unit Testing |  |  |  | Flow Testing |  |  |  |  | multi Company Testing |  |  |  |  | User Guide
|  | YHY | AK | ISA | SYM | HIL | FZ |  |  |  | Dev | UT | FT | MC | SAT | UAT | YHY | AK | HIL | FZ | AIZ | YHY | AK | HIL | FZ | AIZ | YHY | AK | HIL | FZ | TT | SC | BI | BM | Ar
Admin
| User Master | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
| User Master List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
| User Access Right | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
| Log Report |  |  |  | /
| Menu List / Edit | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
System Setup
| Master Code |  |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Terms |  |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| State List | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Country Master List | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
Company Setup
| Create New/Edit/List |  |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT; User Guide BI
| Chart of Account |  | / |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT
| Form Setup |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT
| System General Setup |  | / |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT
| Employee Setup /New/Edit/List | [5 empty] | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT; User Guide BI
| Customer Setup /New/Edit/List | [5 empty] | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT; User Guide BI
| Supplier Setup / New/Edit/List |  | / |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT; User Guide BI
| Project Setup /New/Edit/List | [5 empty] | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT; User Guide BI
| Location Master | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK; User Guide TT
Module : General Ledger | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK; User Guide TT to User Guide BI
Transaction
| Journal Entry | / | bar: Status Dev; User Guide TT
| Duplicate Journal | / | bar: Status Dev; User Guide TT
| Reverse Journal | / | bar: Status Dev; User Guide TT
| Posting Journal | / | bar: Status Dev
Report
| Account Balance Summary | / | bar: Status Dev; User Guide TT
| Trial Balance | / | bar: Status Dev; User Guide TT
| Trial Balance Fiscal Year | / | bar: Status Dev; User Guide TT
| Financial Position Statement | / | bar: Status Dev; User Guide TT
| Income Statement | / | bar: Status Dev; User Guide TT
| Unpost Journal List | / | bar: Status Dev; User Guide TT
| Posted Journal List | / | bar: Status Dev; User Guide TT
| Budget List | / | bar: Status Dev; User Guide TT
Setup
| Financial Year Calendar | / |  |  |  | / | bar: Status Dev; User Guide TT
| Financial Year Calendar List | / |  |  |  | / | bar: Status Dev; User Guide TT
| Budget Entry | / | bar: Status Dev; User Guide TT
| Budget Edit | / | bar: Status Dev; User Guide TT
| Chart Of Account | / |  |  |  | / | bar: Status Dev; User Guide TT
Module : Account Receivable | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK; User Guide TT to User Guide BI
Transaction
| Sales Invoice |  |  |  | / | bar: Status Dev; User Guide TT
Sales Invoice Confirm | bar: Status Dev; User Guide TT
| New Direct Sales Invoice -New, Edit |  |  | / | bar: Status Dev; User Guide TT
New Direct Sales Invoice Confirm | bar: Status Dev; User Guide TT
| Sales Debit Note - New |  |  | / | bar: Status Dev; User Guide TT
| Sales Debit Note Confirm | / |  |  |  |  | / | bar: Status Dev; User Guide TT
| Sales Credit Note |  |  | / | bar: Status Dev; User Guide TT
| Sales Credit Note Confirm | / |  |  |  |  | / | bar: Status Dev; User Guide TT
| Receive Payment |  |  | / | bar: Status Dev; User Guide TT
| Receive Payment Confirm |  |  |  |  | / | bar: Status Dev; User Guide TT
| Copy Sales Invoice |  |  |  | / | bar: Status Dev; User Guide TT
Reports
| Direct Sales Invoice List / Print |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Sales Debit Note List / Print |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Sales Credit Note List / Print |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Receive Payment List / Print |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Customer Statement /Print All & Details | [5 empty] | / | bar: User Guide TT
Setup
| Customer Setup | [5 empty] | / | bar: Status Dev; Unit Testing AK; User Guide TT
Module : Account Payable | bar: Status Dev to multi Company Testing FZ
Transaction
| New Purchase Invoice |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| New Direct Purchase Invoice - New/Edit |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Purchase Invoice Confirm | / |  |  |  |  | / | bar: Status Dev; User Guide TT
| New Purchase Debit Note - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Purchase Debit Note Confirm | / |  |  |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| New Purchase Credit Note - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Purchase Credit Note Confirm | / |  |  |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| New Supplier Payment |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Supplier Payment Confirm | / |  |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| New Other Payment With Item - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Other Payment With Item Confirm | / | bar: Status Dev; Unit Testing AK; User Guide TT
| New Other Payment Without Item - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Bank Reconciliation |  |  |  | / | bar: Status Dev; User Guide TT
| Copy Purchase Invoice |  |  |  | / | bar: Status Dev; User Guide TT
Reports
| Purchase Debit Note List / Print |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Purchase Credit Note List /Print |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Supplier Payment List |  |  |  |  | / | bar: Status Dev; User Guide TT
| Supplier Statement List /Print |  |  |  | / | / | / | bar: Status Dev; User Guide TT
| Other Payment With Item List |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Other Payment Without Item List |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Supplier Payment Advice |  |  | / | bar: Status Dev; User Guide TT
| Purchase Invoice List |  |  |  |  | / | bar: Status Dev; User Guide TT
Setup
Module : Inventory Control | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK; User Guide TT to User Guide BI
Transaction
| Location Transfer - List/Add/Edit | / |  |  | / | bar: Status Dev; User Guide TT
| Location Transfer Confirm |  |  |  | / | bar: Status Dev; User Guide TT
| Item Count And Adjust |  |  |  | / | bar: Status Dev; User Guide TT
| Item Count And Adjust Confirm |  |  |  | / | bar: Status Dev; User Guide TT
| Sales Pricing - Add | / |  |  | / | bar: Status Dev; User Guide TT
Sales Pricing Confirm | bar: User Guide TT
| Purchase Pricing |  |  |  | / | bar: Status Dev; User Guide TT
Purchase Pricing Confirm | bar: User Guide TT
Reports
| Location Transfer List,Print |  |  |  | / | bar: Status Dev; User Guide TT
| Item Adjustment List, Print |  |  |  | / | bar: Status Dev; User Guide TT
| Inventory Planning Report |  |  |  | / | bar: Status Dev; User Guide TT
Inventory Valuation Report | bar: User Guide TT
| Stock Check Report - List/Print | [5 empty] | / | bar: Status Dev; User Guide TT
| Stock Count Sheet |  |  |  | / | bar: Status Dev; User Guide TT
GRN Valuation Report | bar: User Guide TT
Inventory Sales Report | bar: User Guide TT
| Outstanding GRN Report |  |  |  | / | bar: Status Dev; User Guide TT
| Inventory Movement Report |  |  |  | / | bar: Status Dev; User Guide TT
| Inventory List |  |  |  | / | bar: Status Dev; User Guide TT
| Inventory Statement |  |  |  | / | bar: Status Dev; User Guide TT
/
Setup
| Item Category |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Item Type |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Item Details |  | / | bar: Status Dev; User Guide TT
| Item Setup |  | / | bar: Status Dev; Unit Testing AK; User Guide TT
| Unit Of Measure |  | / | bar: Status Dev; User Guide TT
| UOM Conversion |  | / | bar: Status Dev; User Guide TT
| UOM Conversion List |  | / | bar: Status Dev; User Guide TT
Module : Purchasing | bar: Status Dev to multi Company Testing FZ
Transaction
| New Purchase Order - New, Edit |  |  | / | bar: Status Dev; User Guide TT
| New Purchase Order - Confirm |  |  |  |  | / | bar: Status Dev; User Guide TT
| Purchase Receive |  |  | / | bar: Status Dev; User Guide TT
| Receive Item - Confirm |  |  |  |  | / | bar: Status Dev; User Guide TT
Reports
| Purchase Order List , Print All & Details |  |  |  |  | / | / | bar: Status Dev; User Guide TT
| Purchase Receive List |  |  |  |  | / | bar: Status Dev; User Guide TT
Outstanding GRN Report | bar: User Guide TT
Setup
| Suppliers List | [5 empty] | / | bar: Status Dev; User Guide TT
| Unit Of Measures | / | bar: Status Dev; User Guide TT
| UOM Conversion | / | bar: Status Dev; User Guide TT
Module: Good & Services Tax
Transaction
| GAF Files | / | bar: User Guide TT
Setup
| Tax Table | / | bar: Status Dev; User Guide TT
| Tax Class | / | bar: Status Dev; User Guide TT
| Tax Group | / | bar: Status Dev; User Guide TT
| Tax Type | / | bar: Status Dev; User Guide TT
Module : Sales Order | bar: Status Dev to multi Company Testing FZ
Transaction
| Sales Quotation | / | bar: Status Dev; User Guide TT
| Sales Order | / | bar: Status Dev; User Guide TT
| Delivery Order | / | bar: Status Dev; User Guide TT
| Delivery Order Confirm | / | bar: Status Dev; User Guide TT
Reports
| Sales Price | / | bar: Status Dev; User Guide TT
| Sales Quotation List | / | bar: Status Dev; User Guide TT
| Sales Order List | / | bar: Status Dev; User Guide TT
| Delivery Order List | / | bar: Status Dev; User Guide TT
| Sales By Customers | / |  |  |  | / | / | bar: Status Dev; User Guide TT
| Yearly Sales By Customers |  |  |  |  | / | bar: Status Dev; User Guide TT
| Sales By Customer |  |  |  |  | / | bar: Status Dev; User Guide TT
| Sales By Item | / | bar: Status Dev; User Guide TT
| Sales Orders By Customers | / | bar: Status Dev; User Guide TT
| Sales Orders By Item | / | bar: Status Dev; User Guide TT
| Outstanding Sales Orders By Item | / | bar: Status Dev; User Guide TT
Setup
| Sales Price | / | bar: Status Dev; User Guide TT
Module : Zakat & Wakaf | bar: Status Dev to multi Company Testing FZ
Transaction
| Zakat Calculation | / | bar: Status Dev; User Guide TT
| Wakaf Calculation |  |  | / | bar: User Guide TT
Reports
| Nisab Group List | / | bar: Status Dev; User Guide TT
| Zakat Center List | / | bar: Status Dev; User Guide TT
| Zakat Nisab List | / | bar: Status Dev; User Guide TT
| Nisab Group | / | bar: Status Dev; User Guide TT
| Nisab Group Details | / | bar: Status Dev; User Guide TT
| Zakat Center | / | bar: Status Dev; User Guide TT
| Zakat Nisab | / | bar: Status Dev; User Guide TT
| Wakaf Setup |  |  |  |  | / | bar: User Guide TT
| Wakaf Center |  |  |  |  | / | bar: User Guide TT
| Wakaf List |  |  |  |  | / | bar: User Guide TT
| Wakaf Print |  |  |  |  | / | bar: User Guide TT
| Wakaf Entry |  |  | / | bar: User Guide TT
| Wakaf Center | [5 empty] | / | bar: User Guide TT
Module : Setup
Company Setup
| New,List,Edit |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI
| Company Ship To |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI
| Chart Of Account Setup / List |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| Company Business Type |  |  |  | / | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| Form Setup |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| System General Setup |  | / |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| Agent Setup New/Edit/List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI to User Guide BM
| Employee Setup -New,Edit,List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI to User Guide BM
| Customer - New,Edit,List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI
| Customer -Ship To |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI
| Supplier Setup-New,Edit,List |  | / |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI
| Master Code |  | / |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| Project Setup-New,Edit,List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI to User Guide BM
| Terms |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT; User Guide BI to User Guide BM
| Location Master | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| Location List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| State List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK; User Guide TT
| Bank Setup - New, List | [5 empty] | / | bar: Status Dev; User Guide TT; User Guide BI to User Guide BM
| Country Master List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
Module : UserGuide
| UserGuide Content Entry |  |  |  | /
| UserGuide Content Display |  |  | /
| UserGuide Topic Entry |  |  | /
| UserGuide Topic Display |  |  | /
| UserGuide Content Download |  |  | /
| UserGuide Video Play |  |  | / |  | /
| UserGuide Search |  |  | /
| UserGuide Language | [5 empty] | /
Final Stage | bar: Status Dev to multi Company Testing FZ
iFlow
Module homepage
Database reindexing and performance tune up
User Manual
Installation/distribution step and procedure
Note on A3: IT: as at 24/6/2014 13:00
Note on AI5: IT: menu Title
Note on AJ5: IT: Screen Capture
Note on AK5: IT: Content BI
Note on AL5: IT: Content BM
Note on AM5: IT: Content Arabic

## summary
/
iAccount Development Checklist
| Module | Status | [5 empty] | Status
|  | Dev | UT | FT | MC | SAT | UAT
| Admin | / | / |  |  |  |  | 26.67%
| System Setup | / | / | / |  |  |  | 50%
| Company Setup | / | / | / |  |  |  | 50%
| Module : General Ledger | / | [5 empty] | 14.91%
| Module : Account Receivable | / | [5 empty] | 13.54%
| Module : Account Payable | / | [5 empty] | 15.28%
| Module : Inventory Control | / | [5 empty] | 12.22%
| Module : Purchasing | / | [5 empty] | 10.71%
| Module: Good & Services Tax | / | [5 empty] | 9.524%
| Module : Sales Order | / | [5 empty] | 13.33%
| Module : Zakat & Wakaf | / | [5 empty] | 7.407%
| Module : Setup | / | / |  |  |  |  | 20.56%
| Final Stage | [6 empty] | 0%
| average % | 66.9643 | 15.625 | 5.8036 | 0 | 0 | 0 | 18.78%
Note on A2: IT: as at 12/6/2014 13:00

## Sheet2
USER ACCEPTANCE TEST : iACCOUNTS
Company Name | :
Module | :
SCENARIO |  | PROBLEM / RESULT | ACTION