## Sheet1
Prepared student version | duration | start date
•Identify any modules that consists of inventories function | 2 days | 2017-01-04
•Testing & Verification | 2 days | 2017-01-06
•Fixed all debug | 5 days | 2017-01-10
•Re-testing & Verification | 2 days | 2017-01-17
•Installation & database adaptation | 2 days | 2017-01-19
•SPS Installer (Student Version) | 1 day | 2017-01-23
•SPS Installer Licensing | 1 day | 2017-01-24
Prepared student kits
•User manual | 1 day | 2017-01-23
•Certificate | 1 day | 2017-01-23
•SPS Examination | 1 day | 2017-01-23
Training for Lecturer
•User manual | 1 day | 2017-01-23
•Certificate** | 1 day | 2017-01-23
•SPS Examination | 1 day | 2017-01-23