## project
SPS 14.02 supervised by : En. Akmaluddin Mustajid
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | [11 empty] | PERIOD
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | DEVELOPER
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
BACK UP MODULE | [5 empty] | FARID
1st Phase : Feasibility Study
Research | 1 | 4 | 1 | 5 | 100%
Literature Review | 4 | 8 | 4 | 6 | 100%
Analysis
Proposed Solution | 5 | 4 | 5 | 3 | 50%
Presentation 1st Phase
2nd Phase : Design and Specification
Implementation Plan | 6 | 5 | 6 | 7 | 100%
Architecture Design | 6 | 1 | 5 | 8 | 60%
Presentation 2nd Phase | 9 | 3 | 9 | 3 | 0%
3rd Phase : Implementation and Testing
Implementing project | 9 | 3 | 9 | 1 | 0%
Testing | 9 | 4 | 8 | 5 | 1%
Feedback | 10 | 5 | 10 | 3 | 80%
4th Phase : Integration
System integration | 12 | 6 | 12 | 7 | 0%
Presentation Specific Module | 12 | 6 | 12 | 7 | 1%
Completion of Module
BUSINESS INTELLIGENT GRAPH | [5 empty] | SYED
1st Phase : Feasibility Study
Research | 12 | 6 | 8 | 5 | 1%
Literature Review | 12 | 6 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
IMPORT DATA UPLOAD EXCEL | [5 empty] | FIKRI
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
COST CENTRE | [5 empty] | AKMAL/SALIKEEN/DAUS
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
SIMPLIFIED PROCESS | [5 empty] | HIJRAH/FARID/DAUS
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration | 12 | 4 | 8 | 5 | 1%
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
DASHBOARD | [5 empty] | SYED
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
INVENTORY MODULE | [5 empty] | AIZAT/HIJRAH/DAUS
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
SERVICE MODULE | [5 empty] | FADHIRUL/DAUS
1st Phase : Feasibility Study
Rresearch | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
COA REPORT BY LEVEL | [5 empty] | SALIKEEN/FARID /HIJRAH
1st Phase : Feasibility Study | 12 | 4 | 8 | 5 | 1%
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
BUDGET REPORT & SETUP | [5 empty] | AKMAL
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Implementing project | 12 | 4 | 8 | 5 | 1%
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
GST MODULE | [5 empty] | AIZAT/DAUS
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
REPORTING, FIXED ALIGNMENT ON BROWSER | [5 empty] | FADHIRUL/FIKRI/AZRI
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
THEME & BACKGROUND | [5 empty] | HANIF
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
PRINT CHEQUE | [5 empty] | AIZAT
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
EMAIL OPTION | [5 empty] | SALIKEEN/AKMAL
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
AGING BY MONTH | [5 empty] | FARID/HIJRAH
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
AP & AR LEDGER | [5 empty] | FADHIRUL/HIJRAH
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
USER INTERFACE &ALIGNMENT | [5 empty] | FARHANA/NABIHAH/AZRI
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
SPS CLOUD | [5 empty] | AKMAL/AIZAT
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%
DOCUMENTATION | [5 empty] | FARHANA/AZRA
1st Phase : Feasibility Study
Research | 12 | 4 | 8 | 5 | 1%
Literature Review | 12 | 4 | 8 | 5 | 1%
Analysis | 12 | 4 | 8 | 5 | 1%
Proposed Solution | 12 | 4 | 8 | 5 | 1%
Presentation 1st Phase | 12 | 4 | 8 | 5 | 1%
2nd Phase : Design and Specification
Implementation Plan | 12 | 4 | 8 | 5 | 1%
Architecture Design | 12 | 4 | 8 | 5 | 1%
Presentation 2nd Phase | 12 | 4 | 8 | 5 | 1%
3rd Phase : Implementation and Testing
Testing | 12 | 4 | 8 | 5 | 1%
Feedback | 12 | 4 | 8 | 5 | 1%
4th Phase : Integration
System integration | 12 | 4 | 8 | 5 | 1%
Presentation Specific Module | 12 | 4 | 8 | 5 | 1%
Completion of Module | 12 | 4 | 8 | 5 | 1%