## SPS Suport & Development
SPS Support & Development Planing For 2017
|  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
| Audit Scoreboard | Responsibility | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Discussion on Framework & Business Module | Marketing/SPS Support
2 | Prepare Proposal | Marketing/SPS Support
3 | Sent 20 Proposal to client till march | Marketing/SPS Support
4 | Follow up / Meeting / Presentation | Marketing/SPS Support
5 | Customization based on client request | SPS Support/ Programmer
SPS SAGA Bernama
1 | Setup Environment | Programmer
2 | Library | Programmer
3 | DB Design ERD | Programmer
4 | Prototype | SPS Support/ Programmer
5 | Engine | Programmer
6 | User Manual | SPS Support/ Programmer
7 | Testing | SPS Support/ Programmer
SPS System
1 | Study/Enhancemen/Update Version | SPS Support/ Programmer
2 | Sent Update Version | SPS Support/ Programmer
3 | Update Manual Book | SPS Support
SPS in UMT
1 | Discussion With UMT | SPS Support
2 | Discussion / Preparation on Material | SPS Support
3 | Enchement on SPS student version | SPS Support/ Programmer
4 | Marketing & Promotion | Marketing/ Support
5 | Training Start | SPS Support
SPS Lite - Tekun
1 | Study/Enhancement/Update Version
2 | Meet all manager Tekun | Marketing
3 | Enhancement support process | SPS Support
E-Voting System
1 | Developme E-Voting System | Programmer
2 | Discussion on Framework & Business Module | Marketing/SPS Support
3 | Prepare Proposal | Marketing/SPS Support
4 | Sent 10 Proposal to client till march | Marketing/SPS Support
5 | Follow up / Meeting / Presentation | Marketing/SPS Support
6 | Customization based on client request | SPS Support/ Programmer
TAF UMT APPS
1 | Discuss Content
2 | Development
SPS & GST in UiTM
1 | Discussion With UMT | SPS Support
2 | Discussion / Preparation on Material | SPS Support
3 | Training Start | SPS Support/ Programmer
SPS Web Pro

## SPS Marketing
SPS Marketing Planing For 2017
|  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
| Audit Scoreboard | Responsibility | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Discussion on Framework & Business Module | Marketing/SPS Support
2 | Prepare Proposal | Marketing/SPS Support
3 | Sent 20 Proposal to client till march | Marketing/SPS Support
4 | Follow up / Meeting / Presentation | Marketing/SPS Support
5 | Customization based on client request | SPS Support/ Programmer
SPS SAGA Bernama
1 | Setup Environment | Programmer
2 | Library | Programmer
3 | DB Design ERD | Programmer
4 | Prototype | SPS Support/ Programmer
5 | Engine | Programmer
6 | User Manual | SPS Support/ Programmer
7 | Testing | SPS Support/ Programmer
SPS System
1 | Study/Enhancemen/Update Version | SPS Support/ Programmer
2 | Sent Update Version | SPS Support/ Programmer
3 | Update Manual Book | SPS Support
SPS in UMT
1 | Discussion With UMT | SPS Support
2 | Discussion / Preparation on Material | SPS Support
3 | Enchement on SPS student version | SPS Support/ Programmer
4 | Marketing & Promotion | Marketing/ Support
5 | Training Start | SPS Support
SPS Lite - Tekun
1 | Study/Enhancement/Update Version
2 | Meet all manager Tekun | Marketing
3 | Enhancement support process | SPS Support
E-Voting System
1 | Developme E-Voting System | Programmer
2 | Discussion on Framework & Business Module | Marketing/SPS Support
3 | Prepare Proposal | Marketing/SPS Support
4 | Sent 10 Proposal to client till march | Marketing/SPS Support
5 | Follow up / Meeting / Presentation | Marketing/SPS Support
6 | Customization based on client request | SPS Support/ Programmer
TAF UMT APPS
1 | Discuss Content
2 | Development
SPS & GST in UiTM
1 | Discussion With UMT | SPS Support
2 | Discussion / Preparation on Material | SPS Support
3 | Training Start | SPS Support/ Programmer
SPS Web Pro