## Project Planner
TENDER MAMPU SME HI
ACTIVITY | PLAN START | PLAN END | ACTUAL START | ACTUAL END | 2017 | [5 empty] | 2018 | [11 empty] | 2019
[5 empty] | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
PROJECT INITIALIZATION | 2017-08-01 | 2017-08-31 | bar: 2017 Aug
Setup the team and define scope of work | 2017-08-01 | 2017-08-10 | bar: 2017 Aug
Develop high level project plan | 2017-08-05 | 2017-08-10 | bar: 2017 Aug
Define high level requirements | 2017-08-05 | 2017-08-10 | bar: 2017 Aug
Identify and secure key project resources | 2017-08-05 | 2017-08-10 | bar: 2017 Aug
Create project charter | 2017-08-05 | 2017-08-10 | bar: 2017 Aug
Baseline initial resource & project plan | 2017-08-05 | 2017-08-10 | bar: 2017 Aug
Perform Risk Management Plan | 2017-08-05 | 2018-12-31 | bar: 2017 Aug to 2018 Dec
Create project repository | 2017-08-10 | 2017-08-15 | bar: 2017 Aug
Establish project status report | 2017-08-10 | 2017-08-15 | bar: 2017 Aug
Create Issue/Decision Log | 2017-08-10 | 2017-08-15 | bar: 2017 Aug
Create Change Request Log | 2017-08-10 | 2017-08-15 | bar: 2017 Aug
Develop and execute communication plan | 2017-08-10 | 2017-08-15 | bar: 2017 Aug
Conduct kick off meeting with users | 2017-08-15 | 2017-08-15 | bar: 2017 Aug
Setup and configure the development environment | 2017-08-15 | 2017-08-21 | bar: 2017 Aug
Phase Complete (Milestone) | 25/8/2017 | 2017-08-31 | bar: 2017 Aug
REQUIREMENT GATHERING (BRS) | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Determine regulatory compliance approach HKMK | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Requirement study to integrate HKMK and GOSG | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Requirement study to upgrade "Gerbang" | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Requirement study to develop registration portal for registraion agencies. | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Generate requirements Matrix | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Business flows | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Technical flows | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Reconcile high level requirements | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Develop high level business systems design | 2017-09-01 | 2017-09-30 | bar: 2017 Sept
Phase Complete (Milestone) | 2017-09-30 | 2017-09-30 | bar: 2017 Sept
DESIGN AND ANALYSIS | 2017-10-01 | 2017-10-31 | bar: 2017 Oct
Design mock-up screen | 2017-10-01 | 2017-10-15 | bar: 2017 Oct
Design data modelling | 2017-10-15 | 2017-10-25 | bar: 2017 Oct
Redesign business and technical process flows | 2017-10-15 | 2017-10-25 | bar: 2017 Oct
Develop training plan | 2017-10-15 | 2017-10-25 | bar: 2017 Oct
Develop Project contingency plan | 2017-10-15 | 2017-10-25 | bar: 2017 Oct
Develop Code library and script | 2017-10-02 | 2017-10-20 | bar: 2017 Oct
Conduct meeting to demo and evaluate screen mock-up | 2017-10-15 | 2017-10-15 | bar: 2017 Oct
Gain sign off of the screen mock-up | 2017-10-31 | 2017-10-31 | bar: 2017 Oct
Phase Complete (Milestone) | 2017-10-31 | 2017-10-31 | bar: 2017 Oct
APP DEVELOPMENT | 2017-11-01 | 2015-11-30 | bar: 2017 Nov
Build the system core engine | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Build the web apps | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Build the mobile apps | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Build the data migration scripts | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Build the integration module | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Execute user data conversion and system configuration plan | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Test the system integration | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Develop user access matrix | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Develop Unit Testing test plans | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Execute Unit testing test plans | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Develop system & performance testing test plans | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Develop UAT test plans (end to end) | 2017-11-15 | 2017-11-30 | bar: 2017 Nov
Develop input for implementation checklist | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Develop or update user policies and procedures | 2017-11-01 | 2017-11-30 | bar: 2017 Nov
Develop training content | 2017-11-15 | 2017-11-30 | bar: 2017 Nov
Develop the user guide and user manual | 2017-11-15 | 2017-11-30 | bar: 2017 Nov
Phase Complete (Milestone) | 2017-11-30 | 2017-11-30 | bar: 2017 Nov
APPLICATION TESTING | 2017-12-01 | 2017-12-31 | bar: 2017 Dec
Setup the test environment servers and equipment | 2017-12-01 | 2017-12-07 | bar: 2017 Dec
Create remedy request (to move to test environment) | 2017-12-01 | 2017-12-10 | bar: 2017 Dec
Execute System & performance testing test plans and report results | 2017-12-10 | 2017-12-12 | bar: 2017 Dec
Execute Integration testing test plan and report results | 2017-12-10 | 14/12/2017 | bar: 2017 Dec
Execute UAT test plans and report results | 2017-12-17 | 2017-12-25 | bar: 2017 Dec
Develop implementation plan content | 2017-12-17 | 2017-12-31 | bar: 2017 Dec
Review operational readiness | 2017-12-17 | 2017-12-31 | bar: 2017 Dec
Phase Complete (Milestone) | 2017-12-17 | 2017-12-31 | bar: 2017 Dec
IMPLEMENTATION FIRST PILOT | 2018-01-01 | 2018-02-01 | bar: 2018 Jan
Setup and configure the production environment | 2018-01-01 | 2018-01-07 | bar: 2018 Jan
Test the server and network stability | 2018-01-01 | 2018-01-07 | bar: 2018 Jan
Move solution into production environment | 2018-01-01 | 2018-01-07 | bar: 2018 Jan
Execute implementation plan | 2018-01-08 | 2018-01-08 | bar: 2018 Jan
Conduct training | 2018-01-09 | 2018-01-12 | bar: 2018 Jan
Monitor customer / business outcomes | 2018-01-09 | 2018-01-31 | bar: 2018 Jan
Post-Implementation | 2018-01-12 | 2018-01-31 | bar: 2018 Jan
Conduct Post Implementation Review | 2018-01-15 | 2018-01-15 | bar: 2018 Jan
Go Live Monitoring and warranty | 2018-01-31 | 2018-01-31 | bar: 2018 Jan
IMPLEMENTATION 16 AGENCIES
Implementation 4 agencies | 2018-02-01 | 2018-03-31 | bar: 2018 Feb to 2018 Mar
Implementation 4 agencies | 2018-04-01 | 2018-06-30 | bar: 2018 Apr to 2018 Jun
Implementation 4 agencies | 2018-07-01 | 2018-09-30 | bar: 2018 Jul to 2018 Sept
Implementation 4 agencies | 2018-10-01 | 2018-12-31 | bar: 2018 Oct to 2018 Dec
PROJECT CLOSURE | 2019-01-01 | 2019-01-01
Hand over the source code and documentation | 2019-01-01 | 2019-01-01 | bar: 2019 Jan
Audit review benefits and finance | 2019-01-01 | 2019-01-01 | bar: 2019 Jan
Warranty Period | 2019-01-01 | 2019-12-31 | bar: 2019 Jan to 2019 Dec