## Sheet1
iAccount Development Checklist
Module |  | Created By | [5 empty] | Priority | Date Started | Date Completed | Status | [5 empty] | Unit Testing |  |  |  | Flow Testing |  |  |  |  | multi Company Testing
|  | YHY | AK | ISA | SYM | HIL | FZ |  |  |  | Dev | UT | FT | MC | SAT | UAT | YHY | AK | HIL | FZ | AIZ | YHY | AK | HIL | FZ | AIZ | YHY | AK | HIL | FZ
Admin
| User Master | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
| User Master List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
| User Access Right | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
| Menu List / Edit | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK
System Setup
| Master Code |  |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Terms |  |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| State List | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Country Master List | / | bar: Status Dev to Status FT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
Company Setup
| Create New/Edit/List |  |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Chart of Account |  | / |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Form Setup |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| System General Setup |  | / |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Employee Setup /New/Edit/List | [5 empty] | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Customer Setup /New/Edit/List | [5 empty] | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Supplier Setup / New/Edit/List |  | / |  |  |  | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Project Setup /New/Edit/List | [5 empty] | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
| Location Master | / | bar: Status Dev to Status FT; Unit Testing YHY; Flow Testing AK
Module : General Ledger | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
| Journal Entry | / | bar: Status Dev
| Duplicate Journal | / | bar: Status Dev
| Reverse Journal | / | bar: Status Dev
| Posting Journal | / | bar: Status Dev
Report
| Account Balance Summary | / | bar: Status Dev
| Trial Balance | / | bar: Status Dev
| Trial Balance Fiscal Year | / | bar: Status Dev
| Financial Position Statement | / | bar: Status Dev
| Income Statement | / | bar: Status Dev
| Unpost Journal List | / | bar: Status Dev
| Posted Journal List | / | bar: Status Dev
| Budget List | / | bar: Status Dev
Setup | bar: Status Dev
| Financial Year Calendar | / |  |  |  | / | bar: Status Dev
| Financial Year Calendar List | / |  |  |  | / | bar: Status Dev
| Budget Entry | / | bar: Status Dev
| Budget Edit | / | bar: Status Dev
| Chart Of Account | / |  |  |  | / | bar: Status Dev
Module : Account Receivable | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
Sales Invoice
| New Direct Sales Invoice - New, Edit |  |  | / | bar: Status Dev
Sales Invoice Confirm
| Sales Debit Note |  |  | / | bar: Status Dev
Sales Debit Note Confirm
Sales Credit Note
Sales Credit Note Confirm
Receive Payment
| Receive Payment Confirm |  |  |  |  | /
Reports
| Sales Invoice List / Print | [5 empty] | / | bar: Status Dev
| Sales Debit Note List / Print | [5 empty] | / | bar: Status Dev
| Sales Credit Note List / Print | [5 empty] | / | bar: Status Dev
| Receive Payment List / Print |  |  |  |  | / | / | bar: Status Dev
Setup
| Customer Setup | [5 empty] | / | bar: Status Dev; Unit Testing AK
Module : Account Payable | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
| New Purchase Invoice |  |  | / | bar: Status Dev; Unit Testing AK
| New Direct Purchase Invoice - New/Edit |  |  | / | bar: Status Dev; Unit Testing AK
| Direct Purchase Invoice Confirm | [5 empty] | / | bar: Status Dev
| New Purchase Debit Note - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK
| Purchase Debit Note Confirm | / |  |  |  |  | / | bar: Status Dev; Unit Testing AK
| New Purchase Credit Note - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK
| Purchase Credit Note Confirm | / |  |  |  |  | / | bar: Status Dev; Unit Testing AK
| New Supplier Payment |  | / | bar: Status Dev; Unit Testing AK
| Supplier Payment Confirm |  |  |  |  | / | bar: Status Dev; Unit Testing AK
| New Other Payment With Item - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK
Other Payment With Item Confirm | bar: Status Dev; Unit Testing AK
| New Other Payment Without Item - New,Edit |  |  | / | bar: Status Dev; Unit Testing AK
| Other Payment Without Item Confirm | / | bar: Unit Testing AK
Reports
| Purchase Debit Note List / Print |  |  |  |  | / | / | bar: Status Dev
| Purchase Credit Note List /Print |  |  |  |  | / | / | bar: Status Dev
| Supplier Payment List |  |  |  |  | / | bar: Status Dev
| Supplier Statement List /Print |  |  |  |  | / | / | bar: Status Dev
| Other Payment With Item List |  |  |  |  | / | / | bar: Status Dev
| Other Payment Without Item List |  |  |  |  | / | / | bar: Status Dev
| Supplier Payment Advice |  |  | / | bar: Status Dev
| Purchase Invoice List |  |  |  |  | / | bar: Status Dev
Setup
Module : Inventory Control | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
| Location Transfer - List/Add/Edit | / |  |  | / | bar: Status Dev
| Item Count And Adjust |  |  |  | / | bar: Status Dev
Item Count And Adjust Confirm
| Sales Pricing - Add | / |  |  | / | bar: Status Dev
| Purchase Pricing |  |  |  | / | bar: Status Dev
Reports
Count Sheet
Inventory Planning Report
Inventory Valuation Report
Stock Check Report
GRN Valuation Report
Inventory Sales Report
Outstanding GRN Report
Inventory Movement Report
Inventory List
Setup
| Item Category |  | / | bar: Status Dev; Unit Testing AK
| Item Type |  | / | bar: Status Dev; Unit Testing AK
| Item Details |  | /
| Item Setup |  | / | bar: Status Dev; Unit Testing AK
| Unit Of Measure |  | / | bar: Status Dev
| UOM Conversion |  | / | bar: Status Dev
| UOM Conversion List |  | / | bar: Status Dev
Module : Purchasing | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
| New Purchase Order - New, Edit |  |  | / | bar: Status Dev
New Purchase Order - Confirm
| Purchase Receive |  |  | / | bar: Status Dev
Receive Item - Confirm
Reports
| Purchase Order List |  |  |  |  | / | bar: Status Dev
Setup
| Suppliers List | [5 empty] | / | bar: Status Dev
| Unit Of Measures | / | bar: Status Dev
| UOM Conversion | / | bar: Status Dev
Module: Good & Services Tax | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
GAF Files generator
Reports
Setup
| Tax Table | / | bar: Status Dev
| Tax Class | / | bar: Status Dev
| Tax Group | / | bar: Status Dev
| Tax Type | / | bar: Status Dev
Module : Sales Order | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
| Sales Quotation | / | bar: Status Dev
| Sales Quotation List / Print | / | bar: Status Dev
| Sales Order | / | bar: Status Dev
| Sales Order List | / | bar: Status Dev
| Delivery Order | /
| Delivery Order List / Print | /
Reports
| Sales Price | /
Sales By Items
| Sales By Customer | /
Setup
| Sales Price | / | bar: Status Dev
Module : Zakat & Wakaf | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Transaction
Reports
Setup
Module : Setup | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
Company Setup
| New,List,Edit |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Company Ship To |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Chart Of Account Setup / List |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Company Business Type |  |  |  | / | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Form Setup |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| System General Setup |  | / |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Agent Setup New/Edit/List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Employee Setup -New,Edit,List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Customer - New,Edit,List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Customer -Ship To |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Supplier Setup-New,Edit,List |  | / |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Master Code |  | / |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Project Setup-New,Edit,List | [5 empty] | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Terms |  |  |  |  | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Location Master | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Location List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| State List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
| Country Master List | / | bar: Status Dev to Status UT; Unit Testing YHY to Unit Testing AK; Flow Testing AK
Final Stage | bar: Status Dev to Unit Testing HIL; Flow Testing AIZ to Flow Testing AK; multi Company Testing AIZ to multi Company Testing AK
iFlow
Module homepage
Database reindexing and performance tune up
User Manual
Installation/distribution step and procedure
Note on A3: IT: as at 12/6/2014 13:00

## summary
/
iAccount Development Checklist
| Module | Status | [5 empty] | Status
|  | Dev | UT | FT | MC | SAT | UAT
| Admin | / | / |  |  |  |  | 33.33%
| System Setup | / | / | / |  |  |  | 50%
| Company Setup | / | / | / |  |  |  | 50%
| Module : General Ledger | / | [5 empty] | 13.64%
| Module : Account Receivable | / | [5 empty] | 5.072%
| Module : Account Payable | / | [5 empty] | 12.82%
| Module : Inventory Control | / | [5 empty] | 6.173%
| Module : Purchasing | / | [5 empty] | 6.667%
| Module: Good & Services Tax | / | [5 empty] | 4.762%
| Module : Sales Order | / | [5 empty] | 5.556%
| Module : Zakat & Wakaf | [6 empty] | 0%
| Module : Setup | / | / |  |  |  |  | 28.57%
| Final Stage | [6 empty] | 0%
| average % | 46.875 | 15.625 | 5.8036 | 0 | 0 | 0 | 16.66%
Note on A2: IT: as at 12/6/2014 13:00

## Sheet2
USER ACCEPTANCE TEST : iACCOUNTS
Company Name | :
Module | :
SCENARIO |  | PROBLEM / RESULT | ACTION